## Completion_Gates
Area | Status | Evidence
Keyword cleaning and mapping | PASS | 8,118 keyword rows in the canonical 21-sheet workbook
Architecture workbook structure | PASS | 21 required sheets present
Local architecture validation | PASS | 12/12 checks pass
Full dashboard export | PASS | Canonical dashboard is served on port 8602
Planned SEO route implementation | INCOMPLETE | 5/44 planned routes currently match content routes
Embedding semantic validation | BLOCKED | 44/44 pages remain pending-embedding; external transmission requires explicit authorization
Live top-10 SERP validation | BLOCKED | 44/44 pages remain on hold until live SERP evidence is captured
Business evidence and RFQ integration | BLOCKED | Identity, product evidence, commercial terms and RFQ destination are not supplied
Public launch gate | BLOCKED | Private-review/noindex remains correctly active
Git/GitNexus project history | INCOMPLETE | No valid indexed Git repository is available

## Route_Gap
Route | Status
/products/chargers/ | implemented-planned
/products/displayport-cables/ | implemented-planned
/products/hdmi-cables/ | implemented-planned
/products/hubs-docking/ | implemented-planned
/products/usb-cables/ | implemented-planned
/applications/gaming-displayport-cables/ | planned-not-implemented
/applications/gaming-hdmi-cables/ | planned-not-implemented
/oem/displayport-cable-manufacturer/ | planned-not-implemented
/oem/hdmi-cable-manufacturer/ | planned-not-implemented
/oem/usb-c-charger-manufacturer/ | planned-not-implemented
/oem/usb-cable-manufacturer/ | planned-not-implemented
/oem/usb-hub-docking-station-manufacturer/ | planned-not-implemented
/products/chargers/gan/ | planned-not-implemented
/products/chargers/high-power-usb-c/ | planned-not-implemented
/products/displayport-cables/dp-1-4/ | planned-not-implemented
/products/displayport-cables/dp-2-1/ | planned-not-implemented
/products/hdmi-cables/fiber-aoc/ | planned-not-implemented
/products/hdmi-cables/hdmi-2-0/ | planned-not-implemented
/products/hdmi-cables/hdmi-2-1/ | planned-not-implemented
/products/hubs-docking/docking-stations/ | planned-not-implemented
/products/hubs-docking/multiport-usb-c-hubs/ | planned-not-implemented
/products/usb-cables/data-sync/ | planned-not-implemented
/products/usb-cables/high-power-pd/ | planned-not-implemented
/products/usb-cables/usb-a-to-usb-c/ | planned-not-implemented
/products/usb-cables/usb-c-to-usb-c/ | planned-not-implemented
/products/usb-cables/usb4/ | planned-not-implemented
/resources/displayport-cable-buying-guide/ | planned-not-implemented
/resources/displayport-cable-length-guide/ | planned-not-implemented
/resources/displayport-cable-technical-guide/ | planned-not-implemented
/resources/hdmi-cable-buying-guide/ | planned-not-implemented
/resources/hdmi-cable-comparison-guide/ | planned-not-implemented
/resources/hdmi-cable-length-guide/ | planned-not-implemented
/resources/hdmi-cable-technical-guide/ | planned-not-implemented
/resources/usb-c-charger-buying-guide/ | planned-not-implemented
/resources/usb-c-charger-technical-guide/ | planned-not-implemented
/resources/usb-cable-buying-guide/ | planned-not-implemented
/resources/usb-cable-comparison-guide/ | planned-not-implemented
/resources/usb-cable-length-guide/ | planned-not-implemented
/resources/usb-cable-technical-guide/ | planned-not-implemented
/resources/usb-hub-docking-station-comparison-guide/ | planned-not-implemented
/resources/usb-hub-docking-station-technical-guide/ | planned-not-implemented
/solutions/brands-private-label/ | planned-not-implemented
/solutions/retail-ecommerce/ | planned-not-implemented
/solutions/wholesalers-distributors/ | planned-not-implemented
/oem-odm/ | prototype-only-review
/products/ | prototype-only-review
/products/chargers/gan-usb-c-charger/ | prototype-only-review
/products/displayport-cables/displayport-2-1-cable/ | prototype-only-review
/products/hdmi-cables/hdmi-2-1-cable/ | prototype-only-review
/products/hubs-docking/multiport-usb-c-hub/ | prototype-only-review
/products/usb-cables/usb-c-fast-charging-cable/ | prototype-only-review
/products/usb-cables/usb4-cable/ | prototype-only-review
/quality-factory/ | prototype-only-review
/resources/ | prototype-only-review
/solutions/ | prototype-only-review
/solutions/amazon-sellers/ | prototype-only-review
/solutions/importers-distributors/ | prototype-only-review
/solutions/wholesalers/ | prototype-only-review
/terms-of-service/ | prototype-only-review